FIXARS

4-WEEK SPRINT PLAN

MVP Development Sprint

Fixars Core + All 4 Platforms

| Duration | 4 Weeks (28 Days) |
| --- | --- |
| Team Size | 15-20 Engineers |
| Methodology | Agile Sprints (1 week each) |
| Goal | Functional MVP for Alpha Testing |

# Executive Overview

This 4-week sprint delivers a functional MVP of the Fixars ecosystem: the core platform infrastructure plus all four applications (SkillsCanvas, ConceptNexus, InvestDen, CollaBoard) ready for alpha testing.

## Sprint Objectives

- Week 1: Core infrastructure (Identity, Payment, API Gateway)

- Week 2: SkillsCanvas + ConceptNexus MVPs

- Week 3: InvestDen + CollaBoard MVPs

- Week 4: Integration, testing, polish, deployment

## Team Structure

| Team | Size | Focus |
| --- | --- | --- |
| Core Platform | 4 | Identity, Payment, Points, API Gateway, Database |
| SkillsCanvas | 3 | Profiles, verification, matching, engagement |
| ConceptNexus | 3 | Submission, validation, task marketplace |
| InvestDen | 3 | Campaigns, staking, portfolio, oracles |
| CollaBoard | 3 | Rooms, milestones, artifacts, investor view |
| QA / DevOps | 2 | Testing, CI/CD, deployment, monitoring |
| UI/UX | 2 | Design system, mobile UI, responsive web |

## Key Assumptions

- Design mockups completed before sprint starts

- Tech stack decisions finalized (Node.js, React Native, PostgreSQL)

- Payment provider contracts signed (Paystack)

- KYC provider API access ready (Smile ID)

- Development environments configured

# WEEK 1: Foundation

Days 1-7 | Focus: Core Infrastructure

## Core Platform Team (4 engineers)

### Identity Service

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 1-2 | Database schema design (User, Profile, KYC, Session) | Lead | Schema + migrations |
| 1-2 | Auth endpoints (register, login, refresh, logout) | Dev 1 | REST API |
| 3-4 | JWT implementation + session management | Dev 1 | Token system |
| 3-4 | Smile ID integration for KYC Tier 1-2 | Dev 2 | KYC flow |
| 5-6 | Profile CRUD + avatar upload (S3) | Dev 2 | Profile API |
| 5-7 | Reputation engine (scoring algorithm) | Lead | Scoring service |
| 7 | Testing + documentation | All | Unit tests, API docs |

### Payment Service

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 1-2 | Wallet schema + transaction ledger design | Dev 3 | Schema |
| 2-3 | Paystack integration (deposits) | Dev 3 | Deposit flow |
| 3-4 | Escrow engine (create, fund, release, refund) | Dev 4 | Escrow API |
| 4-5 | Payout processing (bank transfers) | Dev 3 | Payout flow |
| 5-6 | Transaction history + statements | Dev 4 | History API |
| 6-7 | Webhook handlers for payment callbacks | Dev 3 | Webhooks |
| 7 | Testing + reconciliation logic | All | Tests |

### API Gateway + Points

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 1-3 | Kong/Express gateway setup + rate limiting | DevOps | Gateway |
| 3-5 | Kafka event bus setup + topic config | DevOps | Event bus |
| 5-7 | Points service (earning rules, balance, history) | Dev 4 | Points API |

## Week 1 Deliverables

- Identity service fully functional with KYC

- Payment service with escrow capability

- API gateway routing all requests

- Event bus publishing/consuming events

- Points service tracking user activity

# WEEK 2: SkillsCanvas + ConceptNexus

Days 8-14 | Focus: Talent + Validation Platforms

## SkillsCanvas Team (3 engineers)

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 8-9 | Skill profile schema + CRUD API | SC Lead | Profile API |
| 8-9 | Skill taxonomy + categories | SC Dev 1 | Taxonomy |
| 10-11 | Skill assessment engine (quizzes) | SC Dev 1 | Assessment |
| 10-11 | Portfolio upload + verification | SC Dev 2 | Portfolio API |
| 12-13 | Talent search + matching algorithm | SC Lead | Matching |
| 12-13 | Engagement flow (propose, accept, complete) | SC Dev 2 | Engagement API |
| 14 | Rating system + proof points | SC Dev 1 | Ratings |

## ConceptNexus Team (3 engineers)

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 8-9 | Concept schema + submission wizard API | CN Lead | Submission API |
| 8-9 | Concept types (Startup, Impact, Side Hustle) | CN Dev 1 | Type config |
| 10-11 | Validation engine (criteria, scoring, matching) | CN Lead | Validation API |
| 10-11 | Validator profiles + domain matching | CN Dev 1 | Validator flow |
| 12-13 | Task marketplace (post, bid, assign) | CN Dev 2 | Task API |
| 12-13 | Task categories + templates | CN Dev 2 | Templates |
| 14 | Validation report generation | CN Lead | Reports |

## UI/UX Team (parallel)

- Mobile app shell (React Native) with navigation

- Design system components (buttons, inputs, cards)

- SkillsCanvas screens (profile, search, engagement)

- ConceptNexus screens (wizard, validation, tasks)

## Week 2 Deliverables

- SkillsCanvas: Create profile, take assessments, search talent, manage engagements

- ConceptNexus: Submit concepts, receive validations, post/complete tasks

- Both integrated with Identity + Payment services

# WEEK 3: InvestDen + CollaBoard

Days 15-21 | Focus: Staking + Execution Platforms

## InvestDen Team (3 engineers)

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 15-16 | Campaign schema + creation flow | ID Lead | Campaign API |
| 15-16 | Campaign types (Concept, Prediction, Challenge) | ID Dev 1 | Type config |
| 17-18 | Stake placement + escrow integration | ID Lead | Staking API |
| 17-18 | Portfolio dashboard + stake tracking | ID Dev 2 | Portfolio API |
| 19-20 | Oracle integration (outcome verification) | ID Dev 1 | Oracle system |
| 19-20 | Payout calculation + distribution | ID Lead | Payout engine |
| 21 | ConceptNexus integration (validated → campaign) | ID Dev 2 | Integration |

## CollaBoard Team (3 engineers)

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 15-16 | Room schema + template-based creation | CB Lead | Room API |
| 15-16 | Room templates (Tech Build, Impact, Creative) | CB Dev 1 | Templates |
| 17-18 | Milestone system (create, track, approve) | CB Lead | Milestone API |
| 17-18 | Task cards + assignment | CB Dev 2 | Tasks |
| 19-20 | Artifact management (upload, version, review) | CB Dev 1 | Artifacts |
| 19-20 | Investor view + progress dashboard | CB Dev 2 | Investor view |
| 21 | InvestDen integration (milestone → escrow release) | CB Lead | Integration |

## UI/UX Team (parallel)

- InvestDen screens (explore, stake, portfolio, campaign)

- CollaBoard screens (room, milestones, artifacts, team)

- Cross-app navigation and deep linking

## Week 3 Deliverables

- InvestDen: Create campaigns, place stakes, track portfolio, receive payouts

- CollaBoard: Create rooms, manage milestones, upload artifacts, investor dashboard

- Cross-platform integrations functional

# WEEK 4: Integration + Launch

Days 22-28 | Focus: Polish, Testing, Deployment

## All Teams

| Day | Task | Team | Deliverable |
| --- | --- | --- | --- |
| 22-23 | Cross-platform event bus integration testing | Core | Integration verified |
| 22-23 | End-to-end user journey testing | QA | Test reports |
| 22-23 | Universal feed + notification system | Core | Feed live |
| 24-25 | Direct messaging (E2E encryption) | Core | DMs working |
| 24-25 | Bug fixes from integration testing | All | Bugs fixed |
| 24-25 | Performance optimization + load testing | DevOps | Load tested |
| 26 | Security audit + penetration testing | DevOps | Security report |
| 26-27 | Production environment setup (AWS) | DevOps | Infra ready |
| 27 | Mobile app submission (TestFlight, Play Store Internal) | UI | Apps submitted |
| 28 | Alpha deployment + team demo | All | Alpha live |

## Week 4 Deliverables

- All 4 apps fully integrated with core platform

- Mobile apps on TestFlight and Play Store internal track

- Web app deployed to production environment

- Monitoring and alerting configured

- Ready for 500-user alpha testing

# Sprint Summary

## MVP Scope Delivered

| Platform | Features |
| --- | --- |
| Fixars Core | SSO, KYC (Tier 1-2), wallet, escrow, points, feed, DMs, notifications |
| SkillsCanvas | Profiles, assessments, search, matching, engagements, ratings |
| ConceptNexus | Submission wizard, validation scoring, task marketplace |
| InvestDen | Campaigns (3 types), staking, portfolio, oracle verification, payouts |
| CollaBoard | Rooms (templates), milestones, artifacts, investor view |

## Out of Scope (Post-Sprint)

- Advanced AI features (success prediction, fraud ML)

- Credit scoring engine

- Diaspora payment rails (USD/GBP)

- USSD interface

- Third-party integrations (GitHub, Figma)

## Risk Factors

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Scope creep | Timeline slip | Strict feature freeze; MVP only |
| Integration issues | Delays | Daily standups; pair programming |
| Payment provider delays | Blocked | Parallel Flutterwave setup |
| Team burnout | Quality | Sustainable pace; no overtime |

## Success Criteria

- All core user journeys functional end-to-end

- 500 concurrent users supported without degradation

- Zero critical security vulnerabilities

- API response times <500ms P95

- Mobile apps approved for internal testing

--- End of Sprint Plan ---